## Sheet1
SERVICE WORK ORDER for Completion by Stardust
Marina Location PAGE, AZ
801-565-1930 Fax
Boat # and Customer Name 1386 | 801-565-1999
Boat Name Water Therapy | Slip
Service Requested | Date | Service Provided / Comments
Need windshield | 2004-12-17 | Completed--OK. CHECKED ON 4/23/05
Need icemaker in fridge | 2004-12-17 | Will install in the spring-- STILL NOT DONE. CHECKED ON 4/23/05
Need new stereo that works with cd changer | 2004-12-17 | Completed--REPLACED WITH NEW UNIT, BUT WORKS ON AN INTERMITTENT BASIS.
WIRE HARNESS CUT VERY SHORT, MANY LOOSE GROUNDS, WON'T WORK
ON A CONSISTANT BASIS.
Need new trim in the back bathroom | 2004-12-17 | Re-visit during spring--STILL NOT DONE. CHECKED ON 4/23/05
Need to re-wire the speakers up on top deck - only port side works | 2004-12-17 | Completed--WIRE CONDUIT WHERE IT LEAVES VERTICAL & GOES ONTO
HORIZONAL NOT CLOSED OFF--WIRING EXPOSED & SUBJECT TO ABRASION.
Rope lighting out in sections | 2004-12-17 | Completed-- OK. CHECKED ON 4/23/05
Topside cushions need reworking | 2004-12-17 | Taking back to Kentucky to re-work--OK. CHECKED ON 4/23/05
Merlin Johnson's comments below:
Lower helm wheel loose on shaft | 2004-12-17 | Completed--OK. CHECKED ON 4/23/05
Many of the plastic latches on the windows are already broken | 2004-12-17 | Contacting manufacturer - This is also a user issue.--WERE TOLD IN JANUARY,
STARDUST WOULD SUPPLY PARTS TO REPAIR OURSELVES. HAVEN'T RECEIVED.
There appears to not be any type of bearing in the swivel on the Davit. | 2004-12-17 | Re-visit during spring--OK. CHECKED ON 4/23/05
Lower rear deck closet molding loose next to sliding door | 2004-12-17 | Completed--OK. CHECKED ON 4/23/05
Oil leak where the lines connect to the Helm wheel control on the upper deck. | 2004-12-17 | Completed--STILL A PROBLEM. LEAKING AT QUICK DISCONNECT AS OF 4/23/05.
Cabinet doors under the sink on the upper deck are sticking and need to be realigned | 2004-12-17 | Completed--OK. CHECKED ON 4/23/05
Depth finders inoperative. | 2004-12-17 | Re-visit when boat is in water--KNOWN ISSUE OF TRANSDUCER RIDING ON
TRAILER BUNK; HAS BEEN MOVED FOR 2005 BOATS. STARDUST AUTHORIZED
MANUFACTURER CHECK OF HEAD UNIT. PROBABLE WASTE OF TIME; STILL
PROBABLE KNOWN TRANSDUCER LOCATION PROBLEM.
A/C filter next to lower Helm not installed properly. It is just lying on the floor | 2004-12-17 | Designed that way - look to a different design in future--FIXED BY WATER
THERAPY INC 4/23/05.
Alternator on Genset not aligned with drive pulleys. May damage other pulleys and belt | 2004-12-17 | Mercruiser rep to look at it--NEVER GOT WESTERBEKE REP OUT. LPM REPAIRED
BILLED TO SUNRISE PEAK??
Main fuel tanks not drawing down at the same rate. STB tanks goes down 2x vs. the Port | 2004-12-17 | Valve adjustment - need to optimize while on water--STARDUST REP EXPLAINED
HOW TO ADJUST PROPERLY. GAUGES READ 1/2 WHEN ACTUALLY 1/4. CAN
SENDING UNITS BE CALIBRATED??
Canvas cover on upper deck is torn and cut. Needs to be redone | 2004-12-17 | Taking back to Kentucky - Replace in the spring time--REDONE AS OF 4/23/05. TIME
WILL TELL IF DONE PROPERLY.
Drawer in forward lower bedroom is stcking and pulling the paneling off. | 2004-12-17 | Completed--??DIDN'T CHECK
Andrew Stuffler's Comments:
The CO sensor in the rear-lower birth appears to be out of calibration and activates whenever the stove is used with the doors and windows closed. My concern is that Someone will disconnect the lower-rear birth sensor and create a potentially dangerous condition. | 2004-12-17 | Believed to be a user issue - using aluminum foil sets the detector off - A user cut the wires and will need to pay to have the CO detector re-wired. This is also a significant liability issue.--REPAIR ON CUT SENSOR REPAIRED BY WATER THERAPY INC. DETECTOR STILL GOING OFF DURING CLEANING WEEKEND WITH NO MOTORS RUNNING.
The outdrives collide with the toy gas tank when the drives are up-and out and the | 2004-12-17 | Design issue - No fix from the manufacturer--OK. CHECKED ON 4/23/05
rudder is ether in a full starboard or port position. This is especially dangerous
due to the lack of an up-and-out indicator at either location.
Screen doors are missing the closing latch function. | 2004-12-17 | Completed--OK. CHECKED ON 4/23/05
Bridge control panel is bowed (improperly installed) | 2004-12-17 | Completed--OK. CHECKED ON 4/23/05
Chair weld has come apart | 2004-12-17 | Couldn't find--OK. CHECKED ON 4/23/05
Leg on couch was deffective | 2004-12-17 | Completed--OK. CHECKED ON 4/23/05
12v van - the chrome is prematurely coming off | 2004-12-17 | Completed--OK. CHECKED ON 4/23/05
No snaps for storage canvas | 2004-12-17 | Spring time fix--WATER THERAPY FIXED 4/23/05.
Radio connections - Antenna location? Radio reception is very poor. | 2004-12-17 | Worked fine for Stardust WHEN CHECKING FROM LPM BASE STATION. NEED TO
TEST ON LAKE FROM DISTANCE.
Cushion missing on starbord storage - never installed | 2004-12-17 | Bring a new one in the spring--STILL MISSING??
What is the plan to deal with plastic latches that continue to break on the windows? | 2004-12-17 | Same as above--SEE 26-27 ABOVE.
Ship to shore radios inoperative | 2004-12-17 | Stardust could not find a problem--SEE 69-70 ABOVE.
Filler neck on aux tank is leaking - damaging carpet | 2004-12-17 | Checked and no leak - Stardust believes that the spills happen because of overfilling the tank--CAN'T ADDRESS ONE WAY OR THE OTHER.
Hinge on storage cabinet up top has problems | 2004-12-17 | Spring fix--NO HINGE. TOP JUST LIFTS OFF AS OF 4/23/05.
Look at hull welds (reinforcement plates) freezing could break weld | 2004-12-17 | Stardust could not find a problem--THERE ARE VOIDS WHERE DECK CONNECTS TO
HULL JUST FORWARD OF HELM; WATER ENTERS HULL. CAULKED BY WATER
THERAPY INC 5/18/05.
Check integetity of carpet (warranty issues or user issues?) | 2004-12-17 | User spills. REPAIRED BY WATER THERPY INC 4/23/05.
Screw missing out of ceiling fan | 2004-12-17 | Completed--OK. CHECKED ON 4/23/05
Hole in front hull - LPM issue | 2004-12-17 | Completed by LPM--OK. CHECKED ON 4/23/05
ITEMS WATER THERAPY DISCOVERED AFTER DEC 17, 2004 STARDUST VISIT
Oven stopped working during trip. Reported to LPM. | 2005-12-02 | BOAT DEWINTERIZED MID APRIL, 2005. WATER THERAPY INC APRIL 23, 2005
WORK WEEKEND FOUND OVEN PULLED OUT & WERE TOLD LPM COULDN'T FIND
PROBLEM AND STARDUST HADN'T AUTHORIZED WARRANTY REPAIR. WTI TOLD
LPM OVEN ON WARRANTY & GET FIXED. 4 WEEKS LATER, 3 DAYS BEFORE 1ST
STILL NOT FIXED. WTI HAD LPM PURCHASE NEW UNIT FOR 1ST TRIP(INSTALLED
IMPROPERLY BY LPM)---NO RANGE/OVEN FOR 1ST OWNER. WATER THERAPY
IS BEING CHARGED $804.94 TO HAVE AN OVEN/RANGE FOR OPENING OF SEASON
DUE TO LACK OF COMMUNICATION BETWEEN STARDUST & LPM.
1st Trip: Boat on shorepower 24 hrs prior to departure. Generator run 6 hrs 1st | 2005-05-19 | WHEN BOAT WENT OUT 1ST SEASON, LPM FOUND AFTER 3 WEEK OUT,
day. Invertor batteries dead 3 am May 20 (all gas dectors going off- low voltage). |  | INVERTOR BATTERIES NOT WIRED TO CHARGE SYSTEM--DO WE HAVE A
PROBLEM NOW WITH BATTERIES OR DOES INVERTOR BANK NOT CHARGE OFF
OF SHOREPOWER?
HVAC Termostat inaccurate by 10-12 degrees. | 2005-05-19 | IS THERMOSTAT CALIBRATABLE?
From 13-15 above. |  | LPM, AFTER 1ST TRIP, CORRECTED WIRING PROBLEM IN SPEAKER SELECTER
SWITCH. WATER THERAPY INC IS BEING CHARGED $240.55. NEED TO MAKE SURE
BILLING AUTHORIZED BY STARDUST.
Numerous owners the past season had complained about a vibration in the | 2005-04-23 | DRIVES WERE PULLED & SERVICED/CHECKED. DRIVESHAFT O-RINGS WERE BADLY
starboard motor/drive. LPM had checked the prop shaft runout (as the starboard |  | WORN & REPLACED. MOTOR ALIGNMENT ON BOTH MOTORS WAS WAY OUT.
prop was damaged mid-season) and found no problem. During our spring work |  | STARBOARD MOTOR COULD NOT BE BROUGHT TO SPECS; MOTOR ALL THE WAY
weekend, we brought in a Mercruiser tech to service/check the drives. |  | DOWN ON THE ADJUSTING SCREWS. MOTOR MOUNTS NEED TO BE LOWER. PORT
MOTOR VERY CLOSE TO BEING SAME WAY WHEN ADJUSTMENT COMPLETED.
AFTER 1ST TRIP 2005, NO MORE VIBRATION.